## tasks
Tasks
This board is where the team will manage their day-to-day sprint tasks. Each task is connected to the epic from the roadmap. Use the different views to plan your next sprint as well as see your current sprint progress.
All Tasks
Name | Sub Tasks | Owner | Status | Priority | Type | Role | Estimated SP | Actual SP | Github link | Task Due Date | Unplanned | Sprint | Item ID | Task Description | Epics | Detailed Spec | Bugs Queue | Active sprint? | Sprint Timeline
Crear tablas base de datos |  | Sergio Alberto Quintero Quiroz | Done | Critical | Feature | Dev | 1 |  |  | 2023-03-07 |  | Sprint 1 | 4128309095 |  | Database |  | Home page loading issue |  | 2023-03-06 - 2023-03-07
Crear inserciones |  | Sergio Alberto Quintero Quiroz | Done | Critical | Feature | Dev | 1 |  |  | 2023-03-07 |  | Sprint 1 | 4128309063 |  | Database |  | Server provides slow response times |  | 2023-03-06 - 2023-03-07
Diseñar interfaz |  | Edward Mora | Done | Critical | Feature | Design | 1 |  | GitHub Integration Guide - https://support.monday.com/hc/en-us/articles/4413247738770-The-New-GitHub-Integration | 2023-03-09 |  | Sprint 2 | 4128309092 | Check the updates of this item |  |  |  |  | 2023-03-08 - 2023-03-09
Programar interfaz |  | Edward Mora | Done | Critical | Feature | Dev | 1 |  |  | 2023-03-09 |  | Sprint 2 | 4128309067 | [5 empty] | 2023-03-08 - 2023-03-09
Vaciado de informacion |  | Sergio Alberto Quintero Quiroz | Done | High | Quality | Product | 1 |  |  | 2023-03-06 |  |  | 4128309103
Crear eliminaciones |  | Sergio Alberto Quintero Quiroz | Done | Critical | Feature | Dev | 1 |  |  | 2023-03-07 |  | Sprint 1 | 4128309089 |  | Database |  |  |  | 2023-03-06 - 2023-03-07
Conectar base de datos |  | Sergio Alberto Quintero Quiroz | Done | Critical | Feature | Dev | 1 |  |  | 2023-03-07 |  | Sprint 1 | 4128353768 |  | Database |  |  |  | 2023-03-06 - 2023-03-07
Llenado de formato IEEE |  | Sergio Alberto Quintero Quiroz | Done | High | Quality | Product | 1 |  |  | 2023-03-06 |  |  | 4128383289
Revision de proyecto 1 |  | Sergio Alberto Quintero Quiroz, Edward Mora | Done | Critical | Test | Product | 1 | 0 |  | 2023-03-07 |  | Sprint 1 | 4128385181 |  | Database |  |  |  | 2023-03-06 - 2023-03-07
Revision 2 |  | Sergio Alberto Quintero Quiroz, Edward Mora | Done | Critical | Test | Product | 1 |  |  | 2023-03-09 |  | Sprint 2 | 4128387621 | [5 empty] | 2023-03-08 - 2023-03-09
Programar buscador de libros |  | Sergio Alberto Quintero Quiroz | Done | Critical | Feature | Dev | 1 |  |  | 2023-03-12 |  | Sprint 3 | 4128389545 | [5 empty] | 2023-03-10 - 2023-03-11
Hacer Tipo de Envio |  | Edward Mora | Done | Critical | Feature | Dev | 1 |  |  | 2023-03-12 |  | Sprint 3 | 4128390138 | [5 empty] | 2023-03-10 - 2023-03-11
Hacer estatus de orden |  | Edward Mora | Done | Critical | Feature | Dev | 1 |  |  | 2023-03-12 |  | Sprint 3 | 4128390346 | [5 empty] | 2023-03-10 - 2023-03-11
Hacer rastreo de orden |  | Edward Mora | Done | Critical | Feature | Dev | 1 |  |  | 2023-03-12 |  | Sprint 3 | 4128390487 | [5 empty] | 2023-03-10 - 2023-03-11
Controlar Pago a Proveedores |  | Edward Mora | Done | Critical | Feature | Dev | 1 |  |  | 2023-03-13 |  |  | 4128391572
Fraccionar Disponibilidad |  | Edward Mora | Done | Critical | Feature | Dev | 1 |  |  | 2023-03-13 |  | Sprint 4 | 4128401602 | [5 empty] | 2023-03-12 - 2023-03-13
Historial de compra para analisis |  | Sergio Alberto Quintero Quiroz | Done | Critical | Feature | Dev | 1 |  |  | 2023-03-13 |  | Sprint 4 | 4128402189 | [5 empty] | 2023-03-12 - 2023-03-13
Analisis para libros mas vendidos |  | Sergio Alberto Quintero Quiroz | Done | Critical | Feature | Dev | 1 |  |  | 2023-03-13 |  | Sprint 4 | 4128402451 | [5 empty] | 2023-03-12 - 2023-03-13
Revision 3 |  | Sergio Alberto Quintero Quiroz, Edward Mora | Done | Critical | Test | Product | 1 |  |  | 2023-03-12 |  | Sprint 3 | 4128404334 | [5 empty] | 2023-03-10 - 2023-03-11
Revision 4 |  | Sergio Alberto Quintero Quiroz, Edward Mora | Done | Critical | Test | Product | 1 |  |  | 2023-03-13 |  | Sprint 4 | 4128413553 | [5 empty] | 2023-03-12 - 2023-03-13
Migrar a BitBucket |  | Edward Mora | Done | Critical | Quality | Product | 1 |  |  | 2023-03-14 |  |  | 4128418850